## GanttChart
PROBLEM CIRCLE
Team Name: | The Jabronis
Start Date: | 2015-06-01 | [5 empty] | 0 | 2015-06-01 | 2015-06-02 | 2015-06-03 | 2015-06-04 | 2015-06-05 | 2015-06-08 | 2015-06-09 | 2015-06-10 | 2015-06-11 | 2015-06-12 | 2015-06-15 | 2015-06-16 | 2015-06-17 | 2015-06-18 | 2015-06-19 | 2015-06-22 | 2015-06-23 | 2015-06-24 | 2015-06-25 | 2015-06-26 | 2015-06-29 | 2015-06-30 | 2015-07-01 | 2015-07-02 | 2015-07-03 | 2015-07-06 | 2015-07-07 | 2015-07-08 | 2015-07-09 | 2015-07-10 | 2015-07-13 | 2015-07-14 | 2015-07-15 | 2015-07-16 | 2015-07-17 | 2015-07-20 | 2015-07-21 | 2015-07-22 | 2015-07-23 | 2015-07-24 | 2015-07-27 | 2015-07-28 | 2015-07-29 | 2015-07-30 | 2015-07-31 | 2015-08-03 | 2015-08-04 | 2015-08-05 | 2015-08-06 | 2015-08-07 | 2015-08-10 | 2015-08-11 | 2015-08-12 | 2015-08-13 | 2015-08-14 | 2015-08-17 | 2015-08-18 | 2015-08-19 | 2015-08-20 | 2015-08-21 | 2015-08-24 | 2015-08-25 | 2015-08-26 | 2015-08-27 | 2015-08-28 | 2015-08-31 | 2015-09-01 | 2015-09-02 | 2015-09-03 | 2015-09-04 | 2015-09-07 | 2015-09-08 | 2015-09-09 | 2015-09-10 | 2015-09-11 | 2015-09-14 | 2015-09-15 | 2015-09-16 | 2015-09-17 | 2015-09-18 | 2015-09-21 | 2015-09-22 | 2015-09-23 | 2015-09-24 | 2015-09-25 | 2015-09-28 | 2015-09-29 | 2015-09-30 | 2015-10-01 | 2015-10-02 | 2015-10-05 | 2015-10-06 | 2015-10-07 | 2015-10-08 | 2015-10-09 | 2015-10-12 | 2015-10-13 | 2015-10-14 | 2015-10-15 | 2015-10-16 | 2015-10-19 | 2015-10-20 | 2015-10-21 | 2015-10-22 | 2015-10-23 | 2015-10-26 | 2015-10-27 | 2015-10-28 | 2015-10-29 | 2015-10-30 | 2015-11-02 | 2015-11-03 | 2015-11-04 | 2015-11-05 | 2015-11-06 | 2015-11-09 | 2015-11-10 | 2015-11-11 | 2015-11-12 | 2015-11-13 | 2015-11-16 | 2015-11-17 | 2015-11-18 | 2015-11-19 | 2015-11-20 | 2015-11-23 | 2015-11-24 | 2015-11-25 | 2015-11-26 | 2015-11-27 | 2015-11-30 | 2015-12-01 | 2015-12-02 | 2015-12-03 | 2015-12-04 | 2015-12-07 | 2015-12-08 | 2015-12-09 | 2015-12-10 | 2015-12-11 | 2015-12-14 | 2015-12-15 | 2015-12-16 | 2015-12-17 | 2015-12-18 | 2015-12-21 | 2015-12-22 | 2015-12-23 | 2015-12-24 | 2015-12-25 | 2015-12-28 | 2015-12-29 | 2015-12-30 | 2015-12-31 | 2016-01-01 | 2016-01-04 | 2016-01-05 | 2016-01-06 | 2016-01-07 | 2016-01-08 | 2016-01-11 | 2016-01-12 | 2016-01-13 | 2016-01-14 | 2016-01-15 | 2016-01-18 | 2016-01-19 | 2016-01-20 | 2016-01-21 | 2016-01-22 | 2016-01-25 | 2016-01-26 | 2016-01-27 | 2016-01-28 | 2016-01-29 | 2016-02-01 | 2016-02-02 | 2016-02-03 | 2016-02-04 | 2016-02-05 | 2016-02-08 | 2016-02-09 | 2016-02-10 | 2016-02-11 | 2016-02-12 | 2016-02-15 | 2016-02-16 | 2016-02-17 | 2016-02-18 | 2016-02-19 | 2016-02-22 | 2016-02-23 | 2016-02-24 | 2016-02-25 | 2016-02-26 | 2016-02-29 | 2016-03-01 | 2016-03-02 | 2016-03-03 | 2016-03-04 | 2016-03-07 | 2016-03-08 | 2016-03-09 | 2016-03-10 | 2016-03-11 | 2016-03-14 | 2016-03-15 | 2016-03-16 | 2016-03-17 | 2016-03-18 | 2016-03-21 | 2016-03-22 | 2016-03-23 | 2016-03-24 | 2016-03-25 | 2016-03-28 | 2016-03-29 | 2016-03-30 | 2016-03-31 | 2016-04-01 | 2016-04-04 | 2016-04-05 | 2016-04-06 | 2016-04-07 | 2016-04-08 | 2016-04-11 | 2016-04-12 | 2016-04-13 | 2016-04-14 | 2016-04-15 | 2016-04-18 | 2016-04-19 | 2016-04-20 | 2016-04-21 | 2016-04-22 | 2016-04-25 | 2016-04-26 | 2016-04-27 | 2016-04-28
Tasks | Start | End | Duration (Days) | Start | End | Duration (Days) | 0: 2015-06-07; 2015-06-05: 2015-06-08; 2015-06-12: 2015-06-15; 2015-06-19: 2015-06-22; 2015-06-26: 2015-06-29; 2015-07-03: 2015-07-06; 2015-07-10: 2015-07-13; 2015-07-17: 2015-07-20; 2015-07-24: 2015-07-27; 2015-07-31: 2015-08-03; 2015-08-07: 2015-08-10; 2015-08-14: 2015-08-17; 2015-08-21: 2015-08-24; 2015-08-28: 2015-08-31; 2015-09-04: 2015-09-07; 2015-09-11: 2015-09-14; 2015-09-18: 2015-09-21; 2015-09-25: 2015-09-28; 2015-10-02: 2015-10-05; 2015-10-09: 2015-10-12; 2015-10-16: 2015-10-19; 2015-10-23: 2015-10-26; 2015-10-30: 2015-11-02; 2015-11-06: 2015-11-09; 2015-11-13: 2015-11-16; 2015-11-20: 2015-11-23; 2015-11-27: 2015-11-30; 2015-12-04: 2015-12-07; 2015-12-11: 2015-12-14; 2015-12-18: 2015-12-21; 2015-12-25: 2015-12-28; 2016-01-01: 2016-01-04; 2016-01-08: 2016-01-11; 2016-01-15: 2016-01-18; 2016-01-22: 2016-01-25; 2016-01-29: 2016-02-01; 2016-02-05: 2016-02-08; 2016-02-12: 2016-02-15; 2016-02-19: 2016-02-22; 2016-02-26: 2016-02-29; 2016-03-04: 2016-03-07; 2016-03-11: 2016-03-14; 2016-03-18: 2016-03-21; 2016-03-25: 2016-03-28; 2016-04-01: 2016-04-04; 2016-04-08: 2016-04-11; 2016-04-15: 2016-04-18; 2016-04-22: 2016-04-25
| Planned Schedule |  |  | Actual Schedule
1) Team Development | 2015-06-08 | 2015-06-15 | 7 | 2015-06-07 | 2015-06-11 | 4
2) Theme Selection or Identification | 2015-06-15 | 2015-06-22 | 7 | 2015-06-11 | 2015-06-15 | 4
3) Activity Plan |  |  | 0 |  |  | 0
4) Description of the Current Situation |  |  | 0 |  |  | 0
5) Goal Setting |  |  | 0 |  |  | 0
6) Root Cause Analysis |  |  | 0 |  |  | 0
7) Root Cause(s) Verification |  |  | 0 |  |  | 0
8) Countermeasure Development & Prioritization |  |  | 0 |  |  | 0
9) PLAN Countermeasure |  |  | 0 |  |  | 0
10) DO Countermeasure Plan |  |  | 0 |  |  | 0
11) CHECK Countermeasure Do |  |  | 0 |  |  | 0
12) ACT On Countermeasure Check |  |  | 0 |  |  | 0
13) Planned Goal vs. Actual Results |  |  | 0 |  |  | 0
14) Planned Activity Schedule vs. Actual |  |  | 0 |  |  | 0
15) Impact Analysis |  |  | 0 |  |  | 0
16) |  |  | 0 |  |  | 0
Note on B4: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on C4: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on E4: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on F4: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.